This is a priority-driven, forward, greedy scheduler for a machine shop. It takes each active part/production order in priority order and places its operations, in sequence, onto machines as early as possible. It respects machine availability, shift hours, working days and raw-material readiness. Each placement is final: the scheduler never goes back to rearrange or fill gaps.

How the scheduling works, step by step

1. Filter what can be scheduled

- It drops operations on "Default" machines (type, make and model all equal "Default").

- It keeps only machines whose WorkCenter.is_schedulable is true.

- It keeps only parts whose PartScheduleStatus.status == 'active'. Everything else goes into the "skipped" list.

2. Decide the order of jobs

- Jobs are sorted by Order.project.priority. A lower number means higher priority. Orders with no project get inf and go last.

- Inside each job, operations are sorted by sequence.

- Delivery date is collected but not used for sorting. It is only used afterwards to report lead_time_difference.

3. Decide when each job can start

- Activation time: each part's start time is PartScheduleStatus.updated_at + 5:30, which converts it to IST. The global start is the earliest activation time, or "now" in IST if there is none.

- Raw material: the material must have status 'Available', or the job is skipped entirely. If raw_material.available_from is in the future, the start is pushed to that time.

- Calendar: Monday to Saturday are working days and Sunday is off. The shift runs from 06:00 to 22:00. (The docstring says 5 PM, but the code uses 22:00.) Any time outside the shift snaps to the next shift start.

4. Place each operation on its machine

For every operation, in sequence:

- Start time = the latest of three things: when the previous operation finished, when the machine becomes available (per its ON/OFF status window), and machine_end_times[machine], which is when that machine's last job ended.

  - The last of these is what stops a machine from being double-booked. Each machine is one resource that runs one job at a time.

- Setup: Operation.setup_time (hours converted to minutes) is added once per operation. If it runs past 22:00, it is split across shifts.

- Processing: Operation.ideal_cycle_time × quantity. The whole batch must finish one operation before the next operation starts. There is no overlapping or transfer-batch flow between operations.

  - Long runs are split shift by shift, with labels like Process(120/500pcs).

- Machine OFF windows: status OFF between available_from and available_to blocks that window. OFF with no end date means the machine is permanently unavailable.

  - find_last_available_operation cuts the routing at the first permanently unavailable machine. The job is then reported as "partially completed".

5. Outputs

- schedule_df: one row per setup or processing segment, with start/end times and quantities.

- The overall end time and total duration, daily production, part status (including lead-time slack in days), and the list of partially completed jobs.

- PDC (probable date of completion) = the maximum end_time per part and production order. It is upserted into the database through upsert_pdc_record.

Parameters that actually drive the schedule

| Parameter | Source | Effect |
| --- | --- | --- |
| Project priority | Order.project.priority | Job order (the main sort key) |
| Operation sequence | sequence / operation_number | Order of operations within a job |
| Setup time | Operation.setup_time | Added once per operation |
| Cycle time | Operation.ideal_cycle_time | × quantity = processing time |
| Quantity | component_quantities | Batch size |
| Activation time | PartScheduleStatus.updated_at | Earliest start per job |
| Raw material status / date | RawMaterial.status, available_from | Hard gate and start delay |
| Machine status window | MachineStatus (ON/OFF, from/to) | Blocks or delays machine use |
| Machine load | machine_end_times (internal) | One job at a time per machine |
| Work center flag | WorkCenter.is_schedulable | Include or exclude machines |
| Calendar | Hardcoded | Mon–Sat, 06:00–22:00 |

Not used for scheduling decisions: the lead_times argument (it gets overwritten by a local variable), the delivery_date (reporting only), the raw_materials dict (built but never read), and the DataFrame's time column. The time column only matters in the look-ahead check; actual durations come from the Operation table.

Things worth knowing (possible bugs)

- No backfilling. machine_end_times only moves forward. A short, low-priority job can't use an idle gap on a machine before a high-priority job's slot.

- Two inconsistent priority sources.

  - part_priorities takes the best priority across all orders with the same part number.

  - The main loop uses each order's own priority.

  - Equal priorities have no tie-breaker, such as delivery date.

- OFF windows shorten the work instead of delaying it. Inside a shift, the code skips the OFF period but keeps the original processing_end. The work that should have been pushed later is effectively lost, so the end time comes out too early.

- Only one status per machine is kept. machine_statuses is a dict, so if a machine has several status records, the last one read wins.

- All units finish at the same time. Every unit gets the last operation's end time, so daily_production puts the whole batch on one day.

- Timezone assumptions.

  - Adding 5:30 to datetime.now() and to updated_at assumes the server and database run in UTC.

  - raw_material.available_from and the machine status times are compared without that conversion.

- Order.get(production_order=...) can fail. It raises an error if more than one order shares a production order number. The PDC step catches this and just prints it.

I can sketch fixes for any of these, such as adding delivery date as a tie-breaker, handling OFF windows correctly, or allowing gap-filling.

Your new scheduler is a big step up from the old one. It is a real finite-capacity engine: it uses a configurable shift calendar, picks among parallel machines or operators, handles batches, interlocks, qualifications and manual pins, and fixes work that is already done or running. It also dropped two things the old one had: priority or due-date sequencing and the raw-material gate. Details below.

How the new scheduling works

The work is split across two files. smt_scheduler.py is the pure engine. smt_schedule_api.py reads the database, prepares the inputs, runs the engine twice, and returns JSON for the Gantt.

1. Build the working calendar (Calendar)

- Shifts come from shift_definition. If that table is empty, they are derived from stage_capacity: start 06:00, plus hours_per_shift × shifts_per_day. Night shifts are supported.

- Days off:

  - Every Sunday.

  - The 1st and 3rd Saturday, but only from April to December.

  - Days in public_holidays.

  - Days in calendar_exceptions (Working, Holiday or Half-Day). A half day keeps the first half of that day's working minutes.

- Runtime changes come from shift_adjustment. They can disable a shift, enable a shift, or add overtime for a date range, either plant-wide or for one operator.

- Per-operator shifts come from operator_shift_assignment.

2. Build resources per stage (_build_resources). Each stage gets one resource mode:

- MACHINE: the machines in equipment_details for that stage.

  - If the stage has needs_operator, a machine can only run while a qualified operator is on shift.

- MANUAL: each qualified operator from operator_step_mapping becomes a resource, with their own shift calendar and MRL expiry.

- FALLBACK: if a stage has neither machines nor operators, it gets one virtual "Unassigned" resource so the plan still has dates.

stage_schedule_config.resource_mode (AUTO, MACHINE or MANUAL) chooses between the first two.

3. Interlocks. These are time windows when a resource is blocked:

| Source | Effect |
| --- | --- |
| Open breakdown | Blocked until mc_ready_date, or forever if no date is set |
| Planned PM (quarterly dates) | Blocked for 8 h from the first shift start that day. If overdue, only a warning |
| Spare or consumable stock ≤ 0 | Blocked until now + procurement lead time, or forever |
| Stock below threshold | Warning only (a flag can make it a block) |
| Stage consumable empty or expired | Whole stage blocked |
| Operator MRL expired | That operator is refused for that stage |

4. Build the orders.

- POs: every PO found in PcbData.productionOrder or in production_order_tracking.

- Part number: the most common part number among the PO's PCBs.

- Routing: product_workflow_mapping, ordered by step_sequence.

- Quantity: the larger of the PCB count and the tracking target_quantity.

- Release time: the earliest PcbData.createdAt, falling back to the tracking start or created time, then to now.

- Duration per operation, in this fallback order:

  - part_process_time.actual_time or sap_time, depending on time_source, falling back to the other one.

  - process_time_seconds from the routing.

  - stage_capacity.manufacturing_time_mins.

  - 1 minute, with a warning.

- SERIES vs BATCH:

  - SERIES operation: one task, taking qty × time per PCB.

  - BATCH operation: ⌈qty / batch_size⌉ tasks (batch size at most 30), each taking the time per batch. These tasks can spread across parallel resources.

5. Placement (run_scheduler and _schedule_op)

- PO order: POs are taken in order of release date, then PO number. This is plain FIFO.

- Operation order: operations run strictly in sequence. Operation k+1 can't start until every piece of operation k has finished.

  - A cooldown is added after an operation if configured. It is measured either in working time or in clock time.

  - A BATCH stage can also be set to release its output only at the next day.

- Choosing a resource for each task:

  - The engine tries every candidate resource for the stage and picks the one with the earliest finish time.

  - Setup minutes are added only when the resource's previous part was different (changeover).

  - A batch of up to 480 minutes is "atomic": it must fit in one unbroken working piece.

- If no resource fits, the engine retries in three passes:

  - Respect all interlocks and MRL expiry.

  - Ignore interlocks.

  - Also ignore MRL expiry.

Tasks placed in pass 2 or 3 are marked blocked and carry the reasons.

- Manual moves: rows in schedule_override are pins. They are reserved first, and everything else is planned around them.

6. Two runs on every request

- Baseline: the theoretical plan from release dates, ignoring progress.

- Current:

  - Finished operations are fixed at their actual times from operator_log.

  - Running operations keep their actual start, and only the remaining work is placed.

  - Pins apply, and nothing new is placed before now.

The response holds both plans (planned vs current), waiting reasons, interlocks, and the conflict notes from detect_conflicts (sequence violations, resource overlaps, tasks running during an interlock).

Parameters that drive the schedule

| Parameter | Source |
| --- | --- |
| PO sequence | Release time (PcbData.createdAt, then tracking dates), then PO number |
| Routing and its order | product_workflow_mapping.step_sequence |
| Duration | part_process_time (actual or SAP), then routing seconds, then stage_capacity |
| Quantity | Count of PcbData rows, or target_quantity if larger |
| SERIES / BATCH | process_type.process_type_batch |
| Batch size, setup, cooldown, next-day release, resource mode, needs operator | stage_schedule_config |
| Resources | equipment_details (machines), operator_step_mapping (operators) |
| Working time | shift_definition, shift_adjustment, operator_shift_assignment, holidays, exceptions |
| Interlocks | machine_breakdown_logs, maintenance_schedules, inventorty_spares, consumables, MRL expiry |
| Progress | operator_log (completed and started counts, actual start and end) |
| Manual moves | schedule_override |
| Runtime knobs | time_source, history_days, plant query parameters, and RULES |

Old vs new

| Aspect | Old scheduling.py | New SMT scheduler |
| --- | --- | --- |
| Sequencing rule | Project priority (lower number first) | FIFO by release date. No priority or due date |
| Which POs are scheduled | Only parts marked active in PartScheduleStatus | Every PO that has a routing |
| Calendar | Hard-coded Mon–Sat, 06:00–22:00 | Configurable shifts, holidays, exceptions, half days, overtime, per-operator shifts |
| Machine choice | Fixed machine_id per operation | Best-finish choice among all resources of the stage (parallel machines) |
| Operators | Not modelled | Can be the resource themselves, or a gate on machines (needs_operator) |
| Batch processing | None (whole quantity as one block) | SERIES and BATCH, split into batches across resources |
| Setup | Once per operation, from the Operation table | On part changeover per resource, from stage config |
| Downtime | One ON/OFF window per machine. Work inside an OFF window was lost | Many interlock blocks per resource. Work is correctly pushed past them |
| Raw material | Must be Available, and start ≥ available_from | Not checked |
| Progress or WIP | Ignored. Always replans from the activation time | Finished work fixed, running work continues, new work starts ≥ now |
| Manual edits | None | Pins via schedule_override |
| Baseline vs actual | No | Planned and current both returned |
| Validation | Only a weekday check | detect_conflicts (sequence, overlap, interlock) |
| Output | Writes a PDC per PO to the DB | Read-only JSON (no PDC written back) |
| Gap filling | No | Still no |

Things to check in the new code

- The same physical machine can be double-booked. add_equipment creates one equipment_details row per stage for the same eqpt_no. _build_resources then turns the duplicates into separate resources (mid-{id}). The scheduler treats them as two independent machines, so it can book that machine on two stages at once. Breakdowns still block both, through the alias map. A fix would be one resource per eqpt_no, valid for several stages.

- MRL expiry is probably never applied. The rest of the app stores and reads operator_MRL_Expiry as MMYY (for example "0127"), using strptime(..., "%m%y"). None of the formats in _parse_date match that, so expiry comes back None.

  - Effect: expired operators are never refused, and the MRL warnings never appear.

  - Fix: add a %m%y branch, after stripping any .0.

- UTC vs local time mix. /operator/updatestatus writes operator_log times with datetime.utcnow(). The scheduler uses local datetime.now() (IST). So actual starts and ends look 5½ hours earlier than they were, and running work is projected wrong.

- Pins ignore interlocks and each other. Pinned tasks are placed with place(res.win_fn, [], ...), which passes no blocks. Two pins can overlap, and a pin can sit inside a breakdown; detect_conflicts only flags it afterwards. The pin's end_time from the override is also ignored, because the duration is recomputed.

- Running work is placed on the baseline machine, not the one actually used. For in-progress operations, the resource comes from plan[op][0] because operator_log has no machine id. If the floor used a different machine, the current plan will show the wrong one.

- Strict operation sequence. A PO's next operation waits for all batches of the previous one. Finished batches can't flow downstream early, which lengthens lead time. This matches your docstring rule, so it is a choice, not a bug.

- Lost from the old version:

  - Priority and delivery date. Consider sorting sequence by priority or due date first, then release date.

  - The raw-material gate.

  - PDC write-back.

- Release time is the PCB upload time. PcbData.createdAt is when the PCB data was uploaded, not when material is ready.

- Performance. Both plans are recomputed on every /schedule/data call, and place() walks windows day by day (horizon of 400 days). With many POs and operator-gated machines (intersect_fn), this will get slow. Caching the result between data changes would help.

I can write the fixes for items 1–4, or add priority/due-date sequencing back into build_schedule.

Partly. Without changing any tables, you can get the correct resource for most cases. The only case you can't resolve exactly is a stage with parallel machines where nothing recorded the machine.

What existing data can give you

| Stage situation | Can you get the real resource? | From where |
| --- | --- | --- |
| MANUAL stage (operator is the resource) | ✅ Exact | operator_log.operator_staff_no. The scheduler's resource is OP-<staff>, so the logged operator is the resource. |
| Stage with only one machine | ✅ Exact | equipment_details: one machine for that stage_id, so every serial at that stage ran on it. |
| FALLBACK (Unassigned) stage | ✅ Trivial | Only one virtual resource exists. |
| Parallel machines, form captures the machine | ✅ Exact | operator_log.log_Data, if the stage's dynamic form has a machine or equipment field. |
| Parallel machines, SPC recorded | ✅ For those serials | spc_data_log has machine_id + stage_id, and referral_number if that holds the serial. |
| Parallel machines, nothing recorded | ❌ Guess only | Today's fallback (the baseline-plan machine) is the best available. |

Check your data first (3 queries)

-- 1. Which stages actually have parallel machines? (only these are a problem)

SELECT stage_id, COUNT(DISTINCT COALESCE(machine_id, eqpt_no)) AS machines

FROM equipment_details GROUP BY stage_id HAVING COUNT(DISTINCT COALESCE(machine_id, eqpt_no)) > 1;

-- 2. Does any form already store a machine in log_Data?

SELECT DISTINCT current_step_id, k

FROM operator_log, jsonb_object_keys("log_Data"::jsonb) AS k

WHERE k ILIKE '%machine%' OR k ILIKE '%eqpt%' OR k ILIKE '%equip%';

-- 3. What does spc_data_log.referral_number contain - serial, PCB id, or PO?

SELECT referral_number, stage_id, machine_id FROM spc_data_log LIMIT 20;

If query 1 returns nothing, every stage is exact already.

Change to build_schedule (no schema change)

Below, a "resolver" means one function that picks each operation's real resource, trying the sources from the table in order.

1. Pull the staff number and form data in the log query:

log_rows = db.query(OperatorLog.PCBserialNoPartNumber, OperatorLog.current_step_id, OperatorLog.Task_Status,

OperatorLog.start_time, OperatorLog.end_time, OperatorLog.operator_name,

OperatorLog.operator_staff_no, OperatorLog.log_Data            # <- added

).join(PcbData, PcbData.PCBserialNoPartNumber == OperatorLog.PCBserialNoPartNumber

).filter(PcbData.productionOrder.isnot(None)).all()

2. Before that loop, build the lookups:

def _staff_key(s):                       # "E169", "e169", "169" -> "169"

return _norm(s).lstrip("e")

# per stage: machine alias -> resource id   (machine_id / eqpt_no, not the name - names repeat)

stage_alias = {}

for sid, lst in stage_resources.items():

stage_alias[sid] = {_norm(a): r.id for r in lst if r.kind == "MACHINE"

for a in (r.id, r.meta.get("eqpt_no")) if a}

def _machine_from_log_data(data, aliases):

if not isinstance(data, dict) or not aliases:

return None

for k, v in data.items():

if not any(t in str(k).lower() for t in ("machine", "eqpt", "equip")):

continue

for x in (v if isinstance(v, list) else [v]):

if isinstance(x, dict):

x = x.get("selectedValue") or x.get("value")

rid = aliases.get(_norm(x))

if rid:

return rid

return None

3. In the progress loop, count staff and machines too. Add two counters to the setdefault dict and fill them:

p = prog.setdefault((po_no, lg.current_step_id), {"done": 0, "started": 0, "start": None, "end": None,

"ops": Counter(), "staff": Counter(), "machines": Counter()})

...

if lg.operator_staff_no:

p["staff"][_staff_key(lg.operator_staff_no)] += 1

m = _machine_from_log_data(lg.log_Data, stage_alias.get(lg.current_step_id))

if m:

p["machines"][m] += 1

4. Add an SPC lookup. This needs SPCDataLog in the imports:

serial_to_po = {_norm(r.PCBserialNoPartNumber.split("$")[0]): r.productionOrder for r in pcb_rows}

serial_to_po.update({_norm(r.PCBserialNoPartNumber): r.productionOrder for r in pcb_rows})

spc_machine = {}

for s in db.query(SPCDataLog.referral_number, SPCDataLog.stage_id, SPCDataLog.machine_id).all():

po = serial_to_po.get(_norm(s.referral_number)) or (s.referral_number if s.referral_number in po_pcbs else None)

rid = stage_alias.get(s.stage_id, {}).get(_norm(s.machine_id))

if po and rid:

spc_machine[(po, s.stage_id)] = rid

5. Keep the counters on each op. In the ops.append({...}) block, add:

"logged_staff": p.get("staff", Counter()), "logged_machines": p.get("machines", Counter()),

6. Add the resolver and use it in fixed:

def actual_resource(op):

sid, cands = op["flow_step_id"], stage_resources.get(op["flow_step_id"], [])

if stage_mode.get(sid) == "MANUAL":                                     # 1. operator is the resource

by_staff = {_staff_key(r.operator): r.id for r in cands if r.kind == "MANUAL" and r.operator}

for staff, _ in op["logged_staff"].most_common():

if staff in by_staff:

return by_staff[staff], "operator_log"

if len(cands) == 1:                                                     # 2. only one resource

return cands[0].id, "single_resource"

if op["logged_machines"]:                                               # 3. machine in form data

return op["logged_machines"].most_common(1)[0][0], "log_data"

rid = spc_machine.get((op["production_order"], sid))                    # 4. SPC entry

if rid:

return rid, "spc_log"

return None, "baseline_plan"                                            # 5. fallback (today's behaviour)

for po in orders.values():

qty = po["quantity"]

for op in po["ops"]:

first = plan[op["op_id"]][0]

rid, src = actual_resource(op)

op["resource_source"] = src

res_id = rid or first["resource_id"]

if op["done"] >= qty:

fixed[op["op_id"]] = {"resource_id": res_id, "start": op["actual_start"] or first["start"],

"end": op["actual_end"] or max(t["end"] for t in plan[op["op_id"]])}

elif op["done"] > 0 or op["started"] > 0:

...  # same remaining-minutes logic as now, but "resource_id": res_id

7. Expose the source to the UI. Add "resource_source": op.get("resource_source") to each operation in the JSON. The Gantt can then show which assignments are confirmed and which are only inferred.

What still can't be recovered

- Parallel-machine stages with no form field and no SPC entry. The data simply doesn't exist, so these stay on the baseline guess, marked baseline_plan.

- BATCH ops spread over two machines. fixed holds one resource per operation, so you get the machine most batches ran on, not a per-batch split.

- Machine logs. If the machine telemetry service (the one sync_with_simulator registers machines with) stores board barcodes from the machine log files, matching those by time would solve the parallel case. That data isn't in this database, so I can't confirm it exists.

One more fix you can make from existing data: operator_log times written by /operator/updatestatus use datetime.utcnow(). Converting them on read (+ timedelta(hours=5, minutes=30) for lg.start_time / lg.end_time) aligns them with the scheduler's local now. Check a few rows against the real shop-floor times first, because older rows may have been written from frontend-supplied times.

Run the three queries and share the results; they decide which of these steps you actually need.

Mostly this happens because the scheduler plans production-order operations, not serials, and it handles work that has already started loosely. There are four separate causes. Which one you're seeing depends on whether the bars on that machine overlap in time or just sit one after another.

1. One bar is a whole PO at a stage (by design)

batch_split makes a single task for a SERIES operation: all serials of the PO, taking qty × time per PCB, on one resource. A BATCH operation becomes chunks of up to 30 serials each.

So a machine row showing many serials one after another is expected: that machine is planned to run the whole PO. If the bars on a machine don't overlap, this is all you're seeing.

2. Started or completed work is put on the baseline machine

For any operation with progress, build_schedule doesn't know which machine was actually used, because no table stores it. It takes the machine from the baseline plan:

first = plan[op["op_id"]][0]

fixed[op["op_id"]] = {"resource_id": first["resource_id"], ...}

The baseline is a theoretical plan built from release dates, so its machine choice is essentially arbitrary. Two POs that really ran in parallel on AOI-1 and AOI-2 can both land on AOI-1 in the Gantt.

3. Started work is placed with no capacity check (the real overlap bug)

In run_scheduler, fixed work is placed with an empty block list and doesn't look at what else is on that machine:

new, e = place(res.win_fn, [], from_t, fx["remaining_minutes"], 0, horizon)   # [] = ignore everything

This causes two kinds of overlap:

- Running POs pile up at "now". Every in-progress PO resumes at max(now, start). If two of them map to the same machine, both bars start at the same moment.

- Scheduled work lands on top of running work. Fixed work isn't reserved up front the way pins are. POs are processed in release order, so an earlier PO's scheduled task can take a slot on a machine. A later PO's running task is then dropped on the same machine at the same time.

4. Completed bars stretch across interleaved POs

For finished work, the bar runs from the first serial's start to the last serial's end (actual_start / actual_end are the min and max over all serials). If PO A and PO B were worked alternately over three days, both bars span those three days and overlap, even on the correct machine.

How to tell which one you have

Each operation in the /schedule/data response has a conflicts list and a status.

| What you see | Cause |
| --- | --- |
| No conflicts, bars one after another | #1 (expected) |
| "Overlaps ... on the same resource" between IN_PROGRESS tasks, or IN_PROGRESS vs SCHEDULED | #2 and #3 |
| "Overlaps ..." between COMPLETED tasks | #2 and #4 (history display only; doesn't affect the future plan) |

Fix for #2 and #3

Reserve all running work before scheduling anything. If the running work's machine is only a guess and that machine is already taken by other running work, move it to a free parallel machine of the same stage.

In smt_scheduler.py → run_scheduler, add this block after the pin reservation loop and before for po_no in sequence::

# Reserve already-running / finished work first, so new work is planned around it.

fixed_slots: Dict[str, Tuple[Resource, datetime, datetime, List[Interval]]] = {}

nb = not_before or datetime.min

for po_no in sequence:

for op in orders[po_no]["ops"]:

fx = fixed.get(op["op_id"]) if fixed else None

if not fx:

continue

cands = stage_resources[op["flow_step_id"]]

res = by_id.get(fx["resource_id"]) or cands[0]

s = fx["start"]

if "remaining_minutes" in fx:

from_t = max(nb, s)

if not fx.get("confirmed"):                      # machine was only a guess

def busy(r):

return any(b > from_t for a, b in reserved.get(r.id, []))

if busy(res):

free = [r for r in cands if not busy(r)]

if free:

res = free[0]                        # spread over parallel machines

new, e = place(res.win_fn, [], from_t, fx["remaining_minutes"], 0, horizon)

segs = (clip_to_windows(res.win_fn, s, from_t) if from_t > s else []) + new

else:

e = max(fx["end"], s)

segs = clip_to_windows(res.win_fn, s, e) if e > s else [(s, e)]

fixed_slots[op["op_id"]] = (res, s, e, segs)

reserved[res.id] += [(a, b) for a, b in segs if b > nb]   # future part blocks the machine

Then, in the main loop, replace the if fx: branch:

if fx:                                                       # history / running work

res, s, e, segs = fixed_slots[op["op_id"]]

tasks = [_task(op, 1, 1, op["quantity"], res, s, e, segs, 0.0, status_fixed=True)]

state[res.id]["free"] = max(state[res.id]["free"], e)

state[res.id]["last_part"] = part

Scheduled tasks already avoid reserved slots (try_res adds reserved.get(res.id, [])), so they now plan around running work.

In smt_schedule_api.py → build_schedule, mark the running work's machine as confirmed only when it is known. This uses the actual_resource() function from my previous reply:

rid, src = actual_resource(op)

...

fixed[op["op_id"]] = {"resource_id": rid or first["resource_id"], "start": ..., "remaining_minutes": ...,

"confirmed": src != "baseline_plan"}

After this:

- Running POs no longer stack on one machine.

- New work never lands on top of running work.

- Any overlap that remains is a genuine data conflict, for example two running POs at a single-machine stage, and detect_conflicts will still flag it.

For #4, the clean fix is to draw completed history per serial (or per batch) from operator_log, not as one PO-wide bar.

If you paste one overlapping pair from the response (both tasks' op_id, status, machine_id and conflicts), I can confirm which cause it is.

I'll combine both files into one standalone service on port 2000. I'll fold in the fixes we discussed, then test it against a small sample database before handing it over.

I'll rerun the setup and testing from scratch, using the real Database_models.py with a temporary SQLite stand-in for Database.py.

That error is a SQLite limitation in my test data (PostgreSQL auto-fills PcbData.ID), not a problem in the service. I'll set the ID explicitly in the seed.

All checks pass. To confirm the fix is what made the difference, I'll run the same scenario through your original two files and compare.

smt_schedule_service.py is the engine and the API combined into one standalone service. I started it on port 2000 against a test database, and both /schedule/health and /schedule/data returned 200.

To run it: put it in the same folder as your Database.py and Database_models.py, then run python smt_schedule_service.py. It needs fastapi, uvicorn, sqlalchemy and pydantic. It also reads .env if python-dotenv is installed, and checks JWTs only when CHECK_JWT_VALIDATION=True, the same way Data_Server.py does.

The endpoints and response format are the same as before, so only the frontend's base URL for /schedule/* needs to change to port 2000. Data_Server.py can keep its include_router line; both services work against the same database.

Fixes included. I ran the same sample data through your original two files and through this one:

| Problem | Original files | This file |
| --- | --- | --- |
| Two production orders running at the same time on a two-machine stage | Both put on AOI-1, overlapping | One on AOI-1, one on AOI-2, no overlaps |
| Operator whose qualification expired (stored as 0125) | Still scheduled | Not used; shows as a blocked interlock |
| Same machine mapped to two stages | Two separate copies that could be double-booked | One machine shared by both stages |
| Machine recorded in the operator's form data | Ignored | Used, and reported as such |

Every operation now has a resource_source field. It tells you whether the machine is confirmed from data or only the old guess (baseline_plan).

One setting to check before going live: /operator/updatestatus saves times in UTC. If your server runs on IST, set OPERATOR_LOG_SHIFT_MINUTES=330 in .env. Look at a few operator_log rows against the real shop-floor times first; I left the default at 0 so nothing changes unless you set it.